## Sheet1
Priority | As a… | I want to be able to… | So that…
0.5 | User | Enter notes for a source | I can remember key details or insights from the source
1 | User | Remove source
1 | User | Remove note
0.5 | User | Upload a source (PDF) | I can enter notes for that source
2 | User | Upload a source (Hosted video) | I can enter notes for that source
2 | User | Upload a source (Image) | I can enter notes for that source
2 | User | Upload a source (Embed video) | I can enter notes for that source
2 | User | Enter a tag for a note | I can organize my notes based on topic
2 | User | Find notes related to a specific tag | I can find my notes related to that topic across all sources
3 | User | Access the system offline | I can work when a network connection is not available (e.g., during plane flight)
4 | User | Share notes with another user | I can share my work on a topic with another user for a shared project
4 | User | Add comments to a note | I can followup on a previous note from either myself or another user
5 | User | Export a list of sources | I can add the sources to an external document bibliography
5 | User | Attach a note to a specific portion of a source | I can identify the relevant portion of the source for the specific note
6 | User | Find sources related to a specific tag | I can find a list of sources related to that topic