## Sheet1
Related User Story | Task Description | Initial Estimate | Amount Remainning After Day…
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Upload a source so that I can enter notes | Fix source display web (Larry) | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Upload a source so that I can enter notes | Fix source display desk (Larry) | 0.25 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Upload a source so that I can enter notes | Research different options for pdf viewing on desk (Larry) | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Upload a source so that I can enter notes | Fix MainPage desktop - source display (Larry) | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
Enter notes for a source so I can remember key details | Fix notes display on web (Bryson) | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enter notes for a source so I can remember key details | Fix notes display on desk (Larry) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Delete a notes I no longer need | Deleting notes on web (Kenneth) | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0
All stories | Logout desktop (Bryson) | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
All stories | Catchup Testing (Kenneth) | 4 | 4 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Delete a source so I can remove sources I don't need | Delete Sources backend (Kenneth +1) | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0
Delete a source so I can remove sources I don't need | Delete Sources frontend (Bryson +1) | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 1.5 | 0 | 0 | 0 | 0
Enter/Delete notes for a source... | Notes DB communication rebood (reach goal for whoever finishes first) | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2
Upload a source so that I can enter notes | Implement adding sources for desktop (Bryson) | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
| Estimate Totals | 26 | 25.5 | 23.5 | 21.5 | 21.5 | 20.5 | 20.5 | 17.5 | 17.5 | 16.5 | 13.5 | 8 | 7 | 7 | 3