## Sheet1
Related User Story | Task Description | Initial Estimate | Amount Remainning After Day…
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
I want to upload a source so that I can review later. | Create login form on desktop. | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I want to upload a source so that I can review later. | Create new user form on desktop. | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
I want to upload a source so that I can review later. | Create Login controller. | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I want to upload a source so that I can review later. | Create model for desktop app. | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I want to upload a source so that I can review later. | Create Mainpage for desktop app | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
I want to upload a source so that I can review later. | Create SourceViewer for desktop | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0.5 | 0.5
I want to upload a source so that I can review later. | Web view for adding and viewing sources | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I want to upload a source so that I can review later. | Configure downloading pdfs for desktop | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0.5 | 0.5
I want to upload a source so that I can review later. | Create new user controller. | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
I want to upload a source so that I can review later. | clean up desktop | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0.5 | 0.5
I want to upload a source so that I can review later. | create mainpage controller | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 | 0 | 0 | 0
I want to upload a source so that I can review later. | Create SourceViewer controller | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 | 0
I want to enter notes on a source so I can remeber key details | Create web api for notes | 2 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 | 0 | 0
I want to enter notes on a source so I can remeber key details | Create web view for adding and viewing notes | 2 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 | 0 | 0.5
I want to enter notes on a source so I can remeber key details | view notes on desktop SourceViewer. | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0 | 0 | 0 | 0.5
I want to enter notes on a source so I can remeber key details | Add notes to desktop model | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
I want to enter notes on a source so I can remeber key details | add notes on desktop SourceViewer | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
All stories | test web app | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1.5 | 1.5
All stories | test desktop app | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
| Estimate Totals | 31 | 28 | 27 | 27 | 25 | 25 | 25 | 24 | 23 | 23 | 20 | 14 | 4 | 4