## Sheet1
Related User Story | Task Description | Initial Estimate | Amount Remaining After Day…
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Upload a source | Allow other source types desktop (Bryson) | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Delete/add Notes for a source | Padding for submit & delete buttons web (Kenneth) | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Delete/add Notes for a source | Add delete button per note (Larry) | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Delete/add Notes for a source | Confirmation deleting - Web (Kenneth) | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Upload a source | Adding source not refreshing list - Desktop (Bryson) | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Upload a source (embed video) | Research embedded videos for desktop (Kenneth) | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Upload a source (embed video) | Implement embedded videos for desktop (Bryson) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
Enter a tag for a note | Note tags - Database (Larry) | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enter a tag for a note | Note tags - Web (Bryson) | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 0
Enter a tag for a note | Note tags - Desktop (Kenneth) | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 2 | 2 | 2 | 0 | 0 | 0 | 0
| Estimate Totals | 12.5 | 12.5 | 12.5 | 10.5 | 9 | 8 | 7 | 7 | 6 | 6 | 6 | 3 | 2 | 1 | 0